## Slide 1: general Project update
Galveston County Consolidated Drainage District
January 28, 2025 Board Meeting

## Slide 2: Clear lake gate and pumps proposal

## Slide 3: Clear lake gate and pumps proposal
Pump station proposed for Clear Creek has proposed capacity of 20,000 cfs (making it one of the largest stations in the world!)
Baseline 2D Hydrodynamic Model Setup and Scenario Analysis
a. Surge Only Scenarios: 100-yr, 500-yr
b. Precipitation Only Scenarios: 10-yr, 25-yr, 100-yr, 500-yr
c. Compound Scenarios
Pump and Gate Scenarios Analysis and Optimalization
- Investigate how pumps and gates configurations can be optimized
- Determine number of pumps required and their capacities
Deliverables include Report and PowerPoint Presentation for Broad Audience
Timeline – 12 Months
Total Cost - $195,0000 (Includes all Indirect Costs)
Planning Level Study
-

## Slide 4: PRECINCT 2 PARTNERSHIP PROGRAM
Maximum Grant Award is 50% Precinct 2 / 50% Local Split
Deadline is February 21, 2025
Must have Funding Identified Fully in Application
Resolution that Includes Funding Required by March 2025
Recommending 2 Applications
  - Lower Clear Creek and Dickinson Bayou
  - Blackhawk Inline and Offline Detention Engineering Design

## Slide 5: Lower clear creek and Dickinson bayou study

## Slide 6: Lower clear creek & Dickinson Bayou feasibility study
Approved in WARDA 2022 but Federal Portion Never Funded
Total Feasibility Study Cost = $3,000,000
Networking to Create Partnerships to get this Study Moving!!!!
Galveston County is Financially Supportive
**Recommend that we Meet with State Politicians to Request up to $1.5 Million
Timeline – 3 Years (36 Months)
Cost - $3,000,000
Feasibility Level Study – Will determine if a project or arrangement of projects provides benefit with a Benefit: Cost Ratio >1
-

## Slide 7: Blackhawk inline and offline detention

## Slide 8: Blackhawk inline and offline detention
Still waiting to hear back from the Texas Water Development Board on our application for engineering design (Flood Infrastructure Fund Preliminary Application)
Precinct 2 Application wants at least a 50% Cost Share from the Applicant
This project is in the State Flood Plan
This project is included in the Galveston County Bond Program
Recommend we put in an Application for Engineering Design indicating we will Pay Up to 50%, but continue pursuing the TWDB Grant and Partnership with Galveston County to see if we can reduce our Cost Share
Timeline – Engineering Design – 12 – 18 Months
Cost - $1,600,000 (Total Est Cost Engineering and Construction $12,810,000)
Engineering Design Level Study

## Slide 9: Friendswood regional detention basin

## Slide 10: Friendswood regional detention basin
Kickoff for Engineering Design in December 2024 (Contractor is Gauge Engineering)
Moving forward with Alternative 2 from Preliminary Engineering (70 Acre Dry Bottom Basin that Avoids Archeological Site)
Submitted Wetland Report for Jurisdictional Determination from USACE for Wetland Sites (4.25 Acres)
Rough Grading Construction 65% (December 2024)
Timeline – Engineering Design – 12 Months
Construction – Will Find Out During Engineering Design – Likely 24-36 Months
Cost – HCFCD Working on Update
GCCDD Cost ($3,500,000 towards Entire Project)
Engineering Design Phase

## Slide 11: Thank you
Samantha Haritos, CFM, ENV SP
Chief Operating Officer of Financial Partnerships, Procurement, and Strategic Planning
Galveston County Consolidated Drainage District
Phone: 832-415-0899
Email: sharitos@gccdd.dst.tx.us